## Slide 1: Project Development & Delivery at TxDOT
Catherine McCreight, MBA
Sr. transportation planner
October 2019

## Slide 2: Key learning objectives
PRELIMINARY DRAFT
…
Understand the many steps and their interdependencies to
successfully develop and construct transportation projects
1
…
  Define how projects are created and move through a funnel as
  part of a portfolio that is actively managed by each district
2
…
3
  Describe how Performance Based Planning facilitates alignment
  of project selections with the department’s strategic objectives
…
4
  Describe how the Quarterly Review Process facilitates accurate tracking of each project’s progress
…
5
  Describe how the Project Delivery & Governance process
  ensures on-time and on-budget completion of projects

## Slide 3: Contents
  Chapter 1: Overview of Project Development and Delivery
    Performance Based Planning
    Quarterly Review Process
    Project Delivery and Governance
  Chapter 2: Project Initiation/Planning
  Chapter 3: Preliminary Engineering
  Chapter 4: Plans, Specifications, and Estimate (PS&E)
  Chapter 5: Letting
  Chapter 6: Construction

## Slide 4: What is project development and delivery?
1
    Project Initiation/ Planning
    Preliminary Engineering
    Plans, Specifications & Estimate
    Letting
    Construction
    Close-out & Maintenance
District Utilities
District ROW
District Environmental
District Railroad Coordinator
Obtain right of entry for environmental study
Begin initial public involvement
Conduct initial public outreach
Provide right of entry from RR to TP&D/DES
Begin title research
Obtain agreement with LPA to contribute ROW funds, if not covered in AFA with LPA
Create core environmental team, including division personnel
Conduct environmental study
Begin technical studies and draft documents
Develop ROW map and identify parcels
Attend utility coordination meeting
Map utilities
Utility verification reimbursable or not reimbursable
Update SUE findings
http://ftp.dot.state.tx.us/pub/txdot/tpp/workflow.pdf

## Slide 5: What is project development and delivery?
1
Focus of this course
The process is cyclical: operations and maintenance identify needs which feed into project selection
Preliminary engineering
Plans, Specifications & Estimate (PS&E)
Letting
Construction
Project
selection
Project initiation
Project
selection
Operations
and maintenance
Operations
and maintenance

## Slide 6
TxDOT Comprehensive Planning and Programming Process
What is project development and delivery?
1
Federal Req’t - MPO/TxDOT
Federal Req’t - TxDOT
State Req’t - TxDOT
State Req’t - TxDOT
Federal Req’t – MPO/TxDOT

## Slide 7: Where do new processes fit?
  Define our planning process and develop scoring criteria and ranking methodology to improve and demonstrate reasons for projects in our 10-year plan and comply with requirements of House Bill 20 (HB20) from 84th Legislative Session
  Build a structure into monitoring the progress of individual projects and the health of each district’s and the department’s portfolio of projects
b
c
  Document our current project development and delivery process and refine it to improve efficiency and facilitate improved staff training
a
  New technology solution to ensure we have accurate data to support performance of these 3 processes and to deliver our transportation program
d
2
  Project Delivery & Governance
  Modernize Portfolio and Project Management
  (TxDOTCONNECT)
  Performance Based Planning
  Quarterly Review Process

## Slide 8: Where do new processes fit?
Manage
(Quarterly Review Process, QRP)
Deliver
(Project Delivery and Governance, PD&G)
Plan
(Performance Based Planning, PBP)
  These processes integrate within project development and delivery in 3 areas that facilitate successful transportation program management and enable TxDOT to meet our transportation goals
2

## Slide 9: Where do new processes fit?
4 - 0
YEAR
Safety
Preservation
Congestion
Connectivity
Construction and maintenance
Projects advance in the funnel as they meet development milestones
Projects that reach the end of the funnel are ready to let and construct
Construct
10 - 5
Preliminary design & environmental
Final design & ROW acquisition
10+
Performance Based Planning Activities
10-year transportation program
Quarterly Review Process Activities
2
Projects are developed with the goal of improving one or more of the four transportation strategic objectives

## Slide 10: Contents
  Chapter 1: Overview of Project Development and Delivery
    Performance Based Planning
    Quarterly Review Process
    Project Delivery and Governance
  Chapter 2: Project Initiation/ Planning
  Chapter 3: Preliminary Engineering
  Chapter 4: Plans, Specifications, and Estimate (PS&E)
  Chapter 5: Letting
  Chapter 6: Construction
  Chapter 7: Summary & Review
A
B
C

## Slide 11: Role of Performance Based Planning (PBP)
  Define clear key performance measure (KPM) goals
  Develop planning targets for each District & MPO
  Align with strategic objectives and support compliance with State Legislative requirements
Plan
(Performance based planning, PBP)
  Districts program a mix of projects to help meet their KPM goals
  Manage portfolio to maintain the right volume and mix of projects
  Defined meeting cadence standardized throughout state
Manage
(Quarterly review process, QRP)
  Standardized workflow
  Track projects from start to finish
  Defined roles and responsibilities
  Pro-active collaboration
  Individual projects are delivered on time and at budgeted cost to minimize delays and cost overruns
Deliver
(Project Delivery and Governance, PD&G)
A

## Slide 12: Role of Performance Based Planning
A
Performance Based Planning
(PBP)
Facilitate adherence to State and Federal rules and regulations
  Enable TxDOT to comply with the performance metric portion of State laws (HB20 , SB312) and Federal requirements (MAP-21 and FAST Act)
  Implement standardized project scoring and selection criteria
A
  Allow TxDOT to optimize allocations among funding categories to maximize alignment of projects in the portfolio to TxDOT’s strategic objectives
Align planning with strategic objectives
B
  Enable TxDOT to monitor impact of previous investment allocation decisions to system performance improvements over a period of time
Enables improved project performance tracking
C

## Slide 13: Performance assessment in project selection
Candidate projects are scored and ranked for its ability to improve system performance aligned with the department’s strategic objectives
2
Plan Authority
(10+ years)
Connectivity
Safety
1
Preservation
2
Congestion
3
4
1
12
11
10
9
8
7
6
5
4
3
2
Funds are allocated across 4 strategic objectives related to departmental goals
Performance assessment process
B
Economy
5
Environment
6
Effects on the Economy and Effects on the Environment are also considered
Corridor
Studies
PBP Initial Scoring

## Slide 14: Examples of Potential Key Performance Measures
A
Safety
Fatalities
Incapacitating Injuries
Safety Project Classification
Hurricane Evacuation Route
Rural Mobility
Connecting Activity Centers
Access to Ports of Entry
Connectivity to Adjacent States
Preservation
Bridge Sufficiency Rating
Roadway Ride Score
Roadway Distress Score
Future Congestion Addressed
Intermodal Connector
Structurally Deficient Bridges Repl.
Connectivity
Current Congestion Addressed
Congestion
New Connectivity

## Slide 15: Stakeholders in Performance Based Planning
Key Stakeholders in PBP Process:
1 State/local elected officials, FHWA/FTA, System users, and any interested party.
A
UTP
TPP
MPOs
QRP Leadership
Committee
Commission
Finance
TRF / MNT /
BRG
Other Interested Parties1,
Districts

## Slide 16: Contents
  Chapter 1: Overview of Project Development and Delivery
    Performance Based Planning
    Quarterly Review Process
    Project Delivery and Governance
  Chapter 2: Project Initiation/ Planning
  Chapter 3: Preliminary Engineering
  Chapter 4: Plans, Specifications, and Estimate (PS&E)
  Chapter 5: Letting
  Chapter 6: Construction
  Chapter 7: Summary & Review
A
B
C

## Slide 17: Importance of QRP for successful portfolio management
  Define clear key performance measure (KPM) goals
  Develop planning targets for each District
  Align with strategic objectives and support compliance with State Legislative requirements
Plan
(Performance based planning, PBP)
  Districts program a mix of projects to help meet their KPM goals
  Manage portfolio to maintain the right volume and mix of projects
  Defined meeting frequency standardized throughout state
Manage
(Quarterly review process, QRP)
  Standardized workflow
  Track projects from start to finish
  Defined roles and responsibilities
  Pro-active collaboration
  Individual projects are delivered on time and at budgeted cost to minimize delays and cost overruns
Deliver
(Project Delivery and Governance, PD&G)
B

## Slide 18: What is the Quarterly Review Process (QRP)?
  Review and update District portfolios
  Meet with Metropolitan Planning Organizations (MPOs)
  Meet with Divisions
  Districts and Central Planning team meet to:
    Review portfolios
    Assess progress against letting schedule
    Assess resource needs and availability
    Prioritize projects
  Central Planning team and QRP Leadership Committee meet to:
    Review consolidated portfolio and District inputs
    Identify and take appropriate actions
Q1
Q4
Q2
Q3
QRM between TxDOT QRP-LC and Central Planning team
Pre-alignment mtg. - Districts & Central Planning team (TPP, FIN, ENV,ROW, PEPS)
District portfolio review
Each quarter is structured around 3 key actions:
B

## Slide 19: Importance of QRP for successful portfolio management
Programming
  There is the right mix and volume of projects programmed at each stage and fiscal year of the funnel to meet planning targets and performance targets for each transportation objective
Milestones
  Monitor progress of letting projects on time, with all milestones cleared (e.g. ROW clearance, environmental clearance, etc.), making the full use of available funds
Resources
  There are enough resources available to Districts and Divisions (internal and external) and they are used effectively to develop the portfolio
Coordination
  All stakeholders have complete visibility into the portfolio and take ownership for their part of the process
There are four desired success outcomes from managing the portfolio:
B
  The QRP enables the achievement of the four outcomes through regular coordination between all stakeholders

## Slide 20: Stakeholders in Quarterly Review Process (QRP)
B
Key Stakeholders in QRP Process:
UTP
TPP
MPOs
QRP Leadership Committee
Commission
Finance
ROW/ENV/ PEPS
Additional Support 1
Districts
1 Design (DES), Construction (CST), Traffic Safety (TRF), Bridge (BRG), Maintenance (MNT), Strategic Planning (STR)
Central Planning Team
    MPO involvement flows through Districts

## Slide 21: Example risks in managing the Department’s portfolio through QRP
B
Implications
Potential Complications
  Projects ready to let - Not having a right-sized funnel with projects “in the hopper” waiting to let
  Timely and accurate data - Gathering key data for the QRP at the last minute
  Delivering with integrity- Prioritizing short term “issue of the day” over QRM focus in the meeting
  Ineffective allocation of resources, especially when additional funding is received
  Lack of time for district pre-meeting reviews, making the Quarterly Review Meeting (QRM) less effective
  QRP relies on specific actions being completed for each QRM, falling behind on one has negative effects on future steps in process

## Slide 22: Contents
  Chapter 1: Overview of Project Development and Delivery
    Performance Based Planning
    Quarterly Review Process
    Project Delivery and Governance
  Chapter 2: Project Initiation/Planning
  Chapter 3: Preliminary Engineering
  Chapter 4: Plans, Specifications, and Estimate (PS&E)
  Chapter 5: Letting
  Chapter 6: Construction
  Chapter 7: Summary & Review
A
B
C

## Slide 23: Successful project delivery through PD&G
  Define clear key performance measure (KPM) goals
  Develop planning targets for each District
  Align with strategic objectives and support compliance with State Legislative requirements
Plan
(Performance based planning, PBP)
  Districts program a mix of projects to help meet their KPM goals
  Manage portfolio to maintain the right volume and mix of projects
  Defined meeting cadence standardized throughout state
Manage
(Quarterly review process, QRP)
  Standardized workflow
  Track projects from start to finish
  Defined roles and responsibilities
  Pro-active collaboration
  Individual projects are delivered on time and at budgeted cost to minimize delays and cost overruns
Deliver
(Project Delivery and Governance, PD&G)
C

## Slide 24: Successful project delivery through PD&G
Early involvement
  Involve all stakeholders early in the project development and delivery process to avoid delays later in the project
Collaboration
  Ensure all stakeholders are collaborating to effectively deliver projects on time and on budget
Parallel processing
  Perform multiple key tasks concurrently (in parallel) to streamline project delivery
Visibility
  Provide the ability for all stakeholders to see project status on all tasks and be aware of all issues from project beginning to project end
There are four guiding principles that ensure successful project delivery:
C
  Successful project delivery occurs when a project is let on schedule and open to the public on time and on budget

## Slide 25: PD&G stakeholders
Key stakeholders in the delivery process:
Districts
MPO
FIN
PEPS
ROW
ENV
TPP
BRG
TRF
DES
Contr-actors
CST
FHWA
C

## Slide 26: Example risks to successful delivery of projects through PD&G
Implications
Potential Complications
  Advancing ROW activities - ROW title work and appraisals aren’t carried out in parallel to environmental clearance
  Accurate tracking of progress and milestones - lack of visibility to all stakeholders early in the process
  Advancing long lead time activities - Railroad agreements are executed late
  Continuous effective collaboration - lack of cooperation between all stakeholders
  ROW clearances are executed late and project gets delayed
  Finding that some activities need more time to complete than initially expected
  Significant delay in Letting date
  Changes are not communicated and create rework
C

## Slide 27: Contents
  Chapter 1: Overview of Project Development and Delivery
  Chapter 2: Project Initiation /Planning
  Chapter 3: Preliminary Engineering
  Chapter 4: Plans, Specifications, and Estimate (PS&E)
  Chapter 5: Letting
  Chapter 6: Construction

## Slide 28: First phase – Project initiation/Planning
  2. Project Authorization
  3. Compliance with planning documents
  5. Agreements & funding identification
Early
involvement
  1. Needs identification
  4. Study requirements determination
Project initiation/ Planning
Preliminary
Engineering
Plans,
specifications &
estimate (PS&E)
Letting
Construction

## Slide 29
Second phase – Preliminary engineering
  4. ENV, IAJR, ROW, and UTL coordination
  3. Schematic development and approval
  1. Data collection / agreements
2. Design concept conference
  5. Public involvement
  6. Value engineering
Project initiation/ Planning
Preliminary
Engineering
Plans,
specifications &
estimate (PS&E)
Letting
Construction
Parallel processing

## Slide 30
Third phase – PS&E
Project initiation/ Planning
Preliminary
Engineering
Plans,
specifications &
estimate (PS&E)
Letting
Construction
  4. PS&E assembly / design review
  3. ENV, IAJR, ROW, UTL, and RR clearances
  2. Detailed design
Collaboration
  1. Finalize alignment and profiles

## Slide 31
Fourth phase – Letting
  1. Letter of authority
  4. Award of contracts
Visibility
  2. Project advertisement
  3. Bidding process
Project initiation/ Planning
Preliminary
Engineering
Plans,
specifications &
estimate (PS&E)
Letting
Construction

## Slide 32
Fifth phase – Construction
  3. Supervision and inspection
  1. Notice to proceed
Project initiation/ Planning
Preliminary
Engineering
Plans,
specifications &
estimate (PS&E)
Letting
Construction
  2. Pre-construction conference
  5. Quality assurance and testing
  6. Change orders
  7. Project acceptance and close-out
  4. Contract Administration
Collaboration

## Slide 33: Summary and Review
Participants should now be able to:
1
…
Understand the many steps and their interdependencies to
successfully develop and construct transportation projects
1

## Slide 34: Key learning objectives
PRELIMINARY DRAFT
Participants should now be able to:
2
…
  Define how projects are created and move through a funnel as
  part of a portfolio that is actively managed by each district
2

## Slide 35: Key learning objectives
Participants should now be able to:
…
3
  Describe how Performance Based Planning facilitates alignment
  of project selections with the department’s strategic objectives

## Slide 36: Key learning objectives
Participants should now be able to:
…
4
  Describe how the Quarterly Review Process facilitates accurate tracking of each project’s progress

## Slide 37: Key learning objectives
PRELIMINARY DRAFT
Participants should now be able to:
…
5
  Describe how the Project Delivery & Governance process
  ensures on-time and on-budget completion of projects

## Slide 38: Questions
Thanks