## Sheet1
Uptown/Memorial Park Connector Path and Bridge Project Development and Implementation Timeline
Calendar Year and Quarter
Project Phase | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4
LONP (Pre-Award Authority) | Calendar Year and Quarter 2019-2: COMPLETED 2019-1
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
Transfer to FTA/Execute Grant | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2020-1
Procure Consultants | bar: Calendar Year and Quarter 2019-2
Kick Off | bar: Calendar Year and Quarter 2019-3
30% | Calendar Year and Quarter 2019-2: COMPLETE
60% | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2020-1
90% | bar: Calendar Year and Quarter 2020-2
95%/100% | bar: Calendar Year and Quarter 2020-3
NEPA | Calendar Year and Quarter 2019-2: COMPLETED 2018-4
Utility Coordination/Relocation | Calendar Year and Quarter 2019-2: N/A
ROW Acquisition | Calendar Year and Quarter 2019-2: N/A
Letting | bar: Calendar Year and Quarter 2020-4