## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  | Data entered by the sponsors | Brazoria | Yes
Project Title | Gessner BOOST |  |  | Data populated/calculated based on inputs | Chambers | No
County | Harris |  |  |  | Fort Bend
Facility/Street Name | Gessner Road |  |  |  | Galveston
TDCs Requested (Y/N) | No |  |  |  | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  | Montgomery
Waller
Planning/Environmental | Q3 FY2019 | Q2 FY2021 | 1059200
Design | Q3 FY2020 | Q2 FY2021 | 443200
Property/ROW Acquisition | N/A | N/A | 294400
Utility Relocation | N/A | N/A
Construction | Q3 FY2020 | Q4 FY2023 | 3303200
Federal Requested |  |  | 5100000
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 1275000
Other |  |  | 0
Total Match |  |  | 1275000
Total Project Cost ('000s) |  |  | 6375000

## Cash Flow CIP Level 2
Gessner BOOST
Project Planned Expenditures (2018 $)
2018-09-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Project ID | Corridor/Project |  |  |  | FY2019 | FY2020 | FY2021 | FY2022 | FY2023 | Total Estimated Cost
46: Gessner BOOST
[10 empty] | 0 | 0
| Planning/Environmental |  | 1323039 |  | 265000 | 728000 | 331000 |  |  | 1324000 | -1000
| Design |  | 553110 |  |  | 277000 | 277000 |  |  | 554000 | -1000
| Property/ROW Acquisition |  | 368740 |  |  | 184000 | 184000 |  |  | 368000 | 1000
| Construction |  | 4129888 |  |  | 619000 | 1239000 | 1239000 | 1032000 | 4129000 | 1000
[10 empty] | 0 | 0
Total - 46: Gessner BOOST |  |  | 6374777 |  | 265000 | 1808000 | 2031000 | 1239000 | 1032000 | 6375000 | 0

## Schedule
Project: Gessner BOOST
|  | FY 2019 |  |  |  | FY 2020 |  |  |  | FY 2021 |  |  |  | FY 2022 |  |  |  | FY 2023
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Phase | Task
Obligate Funds | bar: FY 2019 Q1 to FY 2019 Q4
Program in TIP/STIP | bar: FY 2019 Q1
Request Funds Transfer to FTA | bar: FY 2019 Q2
Letter of No Prejudice | bar: FY 2019 Q3
Open Grant | bar: FY 2019 Q4
Planning & Environmental | bar: FY 2019 Q3 to FY 2021 Q2
Preliminary Concepts | bar: FY 2019 Q3 to FY 2020 Q1
Preferred Concept | bar: FY 2020 Q1
Categorical Exclusion | bar: FY 2020 Q2
Right-of-Way Acquisition | bar: FY 2020 Q3 to FY 2021 Q2
Design | bar: FY 2020 Q3 to FY 2021 Q2
30% Plans | bar: FY 2020 Q3
60% Plans | bar: FY 2020 Q4
90% Plans | bar: FY 2021 Q1
Final Plans | bar: FY 2021 Q2
Construction | bar: FY 2020 Q3 to FY 2023 Q4
Interlocal Agreements | bar: FY 2020 Q3 to FY 2021 Q2
Costruction Procurement | bar: FY 2021 Q3 to FY 2021 Q4
Let for Construction | bar: FY 2022 Q1
Construction | bar: FY 2022 Q2 to FY 2023 Q3
Open for Service | bar: FY 2023 Q4