## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  | Data entered by the sponsors | Brazoria | Yes
Project Title | Little White Oak Bayou Regional Greenway |  |  | Data populated/calculated based on inputs | Chambers | No
County | Harris |  |  |  | Fort Bend
Facility/Street Name | Little White Oak Bayou near I-45 north |  |  |  | Galveston
TDCs Requested (Y/N) | No |  |  |  | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  | Montgomery
Waller
Planning/Environmental | 2020-01-31 | 2021-01-31 | 252251.355
Design | 2021-02-01 | 2022-02-02 | 13470222.3563
Property/ROW Acquisition | 2019-03-31 | 2022-01-01 | TBD
Utility Relocation |  |  | TBD
Construction |  |  | 37615722.0555
Federal Requested |  |  | 51338195.7668
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 12834548.9417
Other |  |  | 0
Total Match |  |  | 12834548.9417
Total Project Cost ('000s) |  |  | 64172744.7084

## LITTLE WHITE OAK CONNECTOR
Houston Parks Board TIP application
Conceptual Cost Estimate
2018-10-28
based on Beyond the Bayous implementation studies cost estimates
LITTLE WHITE OAK BAYOU REGIONAL GREENWAY
TIP Trail segments
| Along | Length (ft) | Type | Cost per linear foot | cost
| Wheatley Street Greenway | 2075.4419 | G1 | 330 | 684895.8409
| Wheatley Street Greenway | 3124.236 | E | 416 | 1299682.1827
| Ferguson Way Greenway | 2880.9797 | E | 416 | 1198487.5406
| Ferguson Way Greenway | 1834.1769 | G1 | 330 | 605278.3866
| Little White Oak Bayou Greenway | 3084.1686 | E | 416 | 1283014.1339
| Little White Oak Bayou Greenway | 5891.1721 | E | 416 | 2450727.5928
| North Shepherd Drive Connection | 125.5 | G1 | 330 | 41415
| Little White Oak Bayou Greenway | 1048.9469 | G1 | 330 | 346152.4813
| Little White Oak Bayou Greenway | 313.1149 | G1 | 330 | 103327.9067
| Little White Oak Bayou Greenway | 1914.4652 | G1 | 330 | 631773.5147
| Little White Oak Bayou Greenway | 1738.3705 | G1 | 330 | 573662.2505
| Little White Oak Bayou Greenway | 713.9746 | G1 | 330 | 235611.6253
| Little White Oak Bayou Greenway | 2981.0329 | G1 | 330 | 983740.8544
| Little White Oak Bayou Greenway | 2796.2894 | G1 | 330 | 922775.4905
| Little White Oak Bayou Greenway | 1450.7816 | G1 | 330 | 478757.9201
| Little White Oak Bayou Greenway | 1179.0697 | G1 | 330 | 389092.998
| Transit Center Connector | 1058.9363 | F | 19 | 20119.7897
| Transit Center Connector | 2402.7487 | F | 19 | 45652.2255
| Little White Oak Bayou Greenway | 1312.9031 | G1 | 330 | 433258.028
| Little White Oak Bayou Greenway | 494.9378 | G1 | 330 | 163329.462
| Little White Oak Bayou Greenway | 233.703 | G1 | 330 | 77121.9983
| Little White Oak Bayou Greenway | 1926.4713 | G1 | 330 | 635735.5412
| Little White Oak Bayou Greenway | 2214.188 | G1 | 330 | 730682.0423
| Little White Oak Bayou Greenway | 888.5113 | G1 | 330 | 293208.7381
| Little White Oak Bayou Greenway | 1189.5265 | G1 | 330 | 392543.7331
| Little White Oak Bayou Greenway | 498.0746 | G1 | 330 | 164364.631
| Little White Oak Bayou Greenway | 470.9139 | G1 | 330 | 155401.599
| Little White Oak Bayou Greenway | 1091.6889 | G1 | 330 | 360257.3208
| Little White Oak Bayou Greenway | 1379.4689 | G1 | 330 | 455224.7294
| Little White Oak Bayou Greenway | 614.3202 | G1 | 330 | 202725.6559
| Little White Oak Bayou Greenway | 309.219 | G1 | 330 | 102042.2555
| Little White Oak Bayou Greenway | 134.3014 | G1 | 330 | 44319.4702
| Little White Oak Bayou Greenway | 421.67 | G1 | 330 | 139151.108
| Little White Oak Bayou Greenway | 1375.5886 | G1 | 330 | 453944.2545
| Little White Oak Bayou Greenway Connector | 674.6822 | G1 | 330 | 222645.1185
| Little White Oak Bayou Greenway | 692.0065 | G1 | 330 | 228362.1292
| Little White Oak Bayou Greenway | 2042.5638 | G1 | 330 | 674046.0692
| Little White Oak Bayou Greenway Connector | 179.2502 | G1 | 330 | 59152.5558
| Moody Park Path (Little White Oak Trail) | 5331.7596 | G1 | 330 | 1759480.6578
| Woodland Park Trail | 393.3705 | G1 | 330 | 129812.2732
| Woodland Park Trail | 744.4644 | G1 | 330 | 245673.2513
| Little White Oak Connector | 875.4082 | G1 | 330 | 288884.7007
| Freed Art and Nature Park Trail (Little White Oak Bayou) | 443.5074 | G1 | 330 | 146357.4407
|  | 11.8458 | MILES |  | 20851892.4977
G1: G type ROW with no need to remove rail
G2: G type ROW with no need to remove rail or pavement
TIP Intersections
| Crossing |  | Type |  | Cost_Tot
| West Mount Houston Rd |  | A |  | 300000
| Dewalt |  | L |  | 5000
| Wheatley |  | L |  | 5000
| Prairie View |  | L |  | 5000
| Knox |  | L |  | 5000
| North |  | L |  | 5000
| Reverend B J Lewis |  | L |  | 5000
| South |  | L |  | 5000
| De Priest |  | L |  | 5000
| Lawn |  | L |  | 5000
| Lawn Bridge over Bayou | 75 | B |  | 800000
| N. Shepherd Park and Ride |  | L |  | 5000
| N. Shepherd Park and Ride |  | L |  | 5000
| Victory |  | A |  | 50000
| W Little York |  | A |  | 300000
| Millville |  | L |  | 5000
| Rittenhouse |  | L |  | 5000
| Granville |  | L |  | 5000
| Dillard |  | L |  | 5000
| Shepherd |  | A |  | 300000
| Stuebner Airline |  | L |  | 5000
| Surratt |  | L |  | 5000
| Yale |  | A |  | 60000
| w Hamilton |  | L |  | 5000
| Tidwell |  | A |  | 300000
| Leago |  | L |  | 5000
| Bridge over Bayou south of Leago St | 100 | B |  | 800000
| Bridge over Bayou north of Werner | 100 | B |  | 800000
| Werner |  | L |  | 5000
| Victoria |  | L |  | 5000
| Whitney |  | L |  | 5000
| Airline |  | A |  | 0
| Crosstimbers |  | A |  | 300000
| Crosstimbers (Transit center connector) |  | A |  | 300000
| North Fwy |  | A |  | 50000
| Fulton (Transit center connector) |  | L |  | 5000
| Placid |  | L |  | 5000
| Bridge over Bayou north of Riggs St | 100 | B |  | 800000
| Riggs |  | L |  | 25000
| Bridge over Bayou north of Stokes | 125 | B |  | 800000
| Bridge over Railroad tracks north of Stokes St | 125 | B |  | 2500000
| Stokes |  | L |  | 60000
| I-610 at I-45 (6 crossings at grade) | 150 | B |  | 4500000
| Sylvester |  | L |  | 5000
| Link |  | L |  | 5000
| Cavalcade |  | A |  | 60000
| Coronado |  | L |  | 5000
| Jewett |  | L |  | 5000
| North Fwy |  | A |  | 50000
| Patton |  | L |  | 25000
| Bridge over Bayou south of Patton St | 250 | B |  | 2500000
| Trimble |  | L |  | 5000
| Bridge over Bayou west of Booth St | 125 | B |  | 800000
| Main St |  | A |  | 50000
| Bridge over I-45 south of North St | 300 | B |  | 4500000
| Wrightwood St |  | L |  | 5000
| Houston Ave |  | L |  | 5000
| White Oak Dr (divided right turn lane) |  | L |  | 5000
21190000
|  |  |  | subtotal intersections and segments | 42041892.4977
|  |  | 20% | Construction Contingency | 8408378.4995
|  |  |  | Construction Cost | 50450270.9972
|  |  | 19.5% | design costs | 9837802.8445
|  |  | 0.5% | plan/env | 252251.355
|  |  |  | Total project | 60540325.1967
|  |  | 6% | mgmt fee | 3632419.5118
|  |  |  | TOTAL COST | 64172744.7084
|  |  |  | Planning / Environmental | 252251.355
|  |  |  | Design | 13470222.3563
|  |  |  | Construction | 50450270.9972
|  |  |  | check | 64172744.7084
|  |  |  | 20% match on construction | 12834548.9417
|  |  |  | construction after match | 37615722.0555

## GREENWAY TYPE COSTS
Houston Parks Board TIP application
Conceptual Cost Estimate - Greenway Type Costs
2018-10-28
based on Beyond the Bayous implementation studies cost estimates
GREENWAY TYPE A
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Pavement Demolition | 15
Curb Demolition | 5
New Curbs | 20
Grading / Storm adjustment | 125
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 445
GREENWAY TYPE B
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Pavement Demolition | 29
Sidewalk Improvements | 80
New Pavement | 480
New Curbs | 80
Grading / Storm adjustment | 125
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 1074
GREENWAY TYPE C
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Pavement Demolition | 20
New Pavement | 400
New Curbs | 40 | new curbs one side
Grading / Storm adjustment | 50
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 790
GREENWAY TYPE D
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 340 | 2 x 10' wide concrete trails
Pavement Demolition | 56
New Pavement | 520
Grading / Storm adjustment | 125
Planting | 220 | 5'-6' planting both sides of trail x 2 trails
Total Cost per LF | 1261
GREENWAY TYPE E
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Parking Lot modification | 11
Retaining Wall | 75
Grading / Storm adjustment | 50
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 416
GREENWAY TYPE E1
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Parking Lot modification | 11
Grading / Storm adjustment | 50
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 341
GREENWAY TYPE F
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Pavement marking | 1 | paint
Intersection Transition | 16
Street Signage | 2
Total Cost per LF | 19
GREENWAY TYPE G1
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Grading / Storm adjustment | 50
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 330
GREENWAY TYPE H
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 340 | two 10' wide concrete trails
Pavement Marking | 15
Grading / Storm adjustment | 50
Planting | 220 | 5'-6' planting both sides of trail x 2 trails
Total Cost per LF | 625