## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  |  | Data entered by the sponsors | Brazoria | Yes
Project Title | FM1314 Extension & Airport Road Widening |  |  |  | Data populated/calculated based on inputs | Chambers | No
County | Montgomery |  |  |  |  | Fort Bend
Facility/Street Name | FM1314 & Airport Road |  |  |  |  | Galveston
TDCs Requested (Y/N) | No |  |  |  |  | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  |  | Montgomery
Waller
Planning/Environmental | 2020-07-01 | 2021-03-31 | 0
Design | 2020-10-01 | 2022-03-31 | 1234.147 | 1234147
Property/ROW Acquisition | 2021-04-01 | 2022-03-31 | 63.231 | 63231
Utility Relocation | 2020-07-01 | 2022-03-31 | 0
Construction | 2022-07-01 | 2024-07-01 | 10781.563 | 10781563
Federal Requested |  |  | 12078.941
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 5390.345 | 5390345
Other |  |  | 0
Total Match |  |  | 5390.345
Total Project Cost ('000s) |  |  | 17469.286