## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  | Data entered by the sponsors | Brazoria | Yes
Project Title | Angleton Alternative Mode Connectivity Project |  |  | Data populated/calculated based on inputs | Chambers | No
County | Brazoria |  |  |  | Fort Bend
Facility/Street Name | Various |  |  |  | Galveston
TDCs Requested (Y/N) | No |  |  |  | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  | Montgomery
Waller
Planning/Environmental | Dec 31 2018 | Oct 1 2019 | 0
Design | Oct 31 2020 | MAR 31 2021 | 397840.856
Property/ROW Acquisition | N/A | N/A | 0
Utility Relocation | N/A | N/A | 0
Construction | SEP 1 2021 | MAR 1 2022 | 2466613.3072
Federal Requested |  |  | 2864454.1632
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 716113.5408
Other |  |  | 0
Total Match |  |  | 716113.5408
Total Project Cost ('000s) |  |  | 3580567.704