## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  |  | Data entered by the sponsors | Brazoria | Yes
Project Title | Brazoswood & Lazy Lane School Access Improvements |  |  |  | Data populated/calculated based on inputs | Chambers | No
County | Brazoria |  |  |  |  | Fort Bend
Facility/Street Name | Lazy Lane and Brazoswood Drive |  |  |  |  | Galveston
TDCs Requested (Y/N) | No |  |  |  |  | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) | Federal only |  | Montgomery
Waller
Planning/Environmental | 2020-07-01 | 2020-12-31 | 28 | 28000
Design | 2020-07-01 | 2021-06-30 | 260.057 | 260057
Property/ROW Acquisition | 2021-01-01 | 2021-03-31 | 0 | If needed
Utility Relocation | 2020-04-01 | 2021-06-30 | 0 | If needed
Construction | 2021-10-01 | 2022-10-01 | 2485.886 | 2485886
Federal Requested |  |  | 2773.943 | 2773943
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 693.486 | 693486
Other |  |  | 0
Total Match |  |  | 693.486
Total Project Cost ('000s) |  |  | 3467.429