## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  | Data entered by the sponsors | Brazoria | No
Project Title | Traffic Signal Integration |  |  | Data populated/calculated based on inputs | Chambers | No
County | Harris |  |  |  | Fort Bend | No
Facility/Street Name | Business 90, FM 2100, and FM 1942 |  |  |  | Galveston | No
TDCs Requested (Y/N) |  |  |  |  | Harris | Yes
[5 empty] | Liberty | No
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  | Montgomery | No
[5 empty] | Waller | No
Planning/Environmental |  |  | 0
Design | 2026-01-01 | 2027-01-01 | 68
Property/ROW Acquisition |  |  | 0
Utility Relocation |  |  | 0
Construction | 2027-01-01 | 2029-01-01 | 1292
Federal Requested |  |  | 1360
Local/State Match ('000s)
State |  |  | 340
Local - General Revenue
Other |  |  | 0
Total Match |  |  | 340
Total Project Cost ('000s) |  |  | 1700